## Decommission
GISA Decommission Project
项目状态周报/Weekly Project Status Report
As of Date 2012 Mar. 19th
Project Name: |  |  | ALU QingDao GISA Decommission Project
CIO Project Manager |  |  | Sandy Xin |  |  |  | Sponsoring Department: | OP/FI
CG Project Manager |  |  | Den Xue
填写人/Author
Ya Shen
Status
Overall Status: |  |  |  | Comments:
Green
This week Major Issues/Risks
# | Item |  |  |  |  | Required Action |  | Responsible | Timing
1 | Global interface |  |  |  |  | IVS's equirement to be identified and confirmed |  | Interface owner
Key Metrics
|  | This Week |  | Last Week | Reference: Issues / Risks
| Schedule | Green
| Effort | Green
| Resources | Green
| Requirements | Green
| Change Requests | Green
| Issues | Green
| Risks | Yellow |  |  | Global Interface Support
| Quality | Green
| Open Defects | Not Applicable |  | Not Applicable
No. | This week Main Jobs | [5 empty] | Remark
1 | Build Gate Review Meeting | [5 empty] | Build Gate Passed
2 | Cut Over Methodology Meeting | [5 empty] | Communicate Cut-Over plan and approach with user
3 | Master Data collection : requirement and restraints communication with cost team | [5 empty] | Pre-load master data (Material master, BOM, Routing, Drawing) into PRD prior to period end
4 | Master Data collection precheck | [5 empty] | Pre-load master data (Material master, BOM, Routing, Drawing) into PRD prior to period end
5 | UAT in Sandbox | [5 empty] | UAT(User Acceptance Testing) : 1. UAT Test Script: 80% completed 2. Seperated Scenario: 100% completed
Activities for next week
No. | Functional Area |  | Activity |  |  |  |  | Owner | Due Date
1 | SAP |  | UAT |  |  |  |  | OP team & Project team | 2012/3/20
2 | SAP |  | Master data collection |  |  |  |  | Kevin Sun/ ASB QD users/ Shen Ya | 2012/3/23
3 | SAP |  | User training |  |  |  |  | Project team | 2012/3/23
4 | SAP |  | Cut over and Mock plan |  |  |  |  | Sandy/ Shen Ya | 2012/3/19
5 | Global interface |  | Submit CR list |  |  |  |  | Zhou Daniel | 2012/3/20
6 | SAP |  | To apply for data conversion accout in PRD |  |  |  |  | Ji Hong/ Shen ya | 2012/3/20
7 |  |  | Back Out Plan |  |  |  |  | Sandy/ Shen Ya | 2012/3/23
8 |  |  | Client refresh for Mock |  |  |  |  | Sandy | 2012/3/25
9 |  |  | Transport CR into PRD |  |  |  |  | Wu Qiang | 2012/3/25
10 |  |  | Discussion on Transaction Data template and key points |  |  |  |  | Project team | 2012/3/20
11 | Support |  | 1. Modify WiFi Interface 2. Confirm the test schedule with Global Interface team & key business teams 3. Set the authorities for the new added T-codes. 4. Master data collection |  |  |  |  | Angel Xu
Process QA Notes
No. | Process Area |  | Notes
1
2
3
4
5
6

## Sheet1
BA：